## Slide 1
SUEDE DESIGNATHON 2026
WIN THE WEEKEND.
A competition operating plan for
Ethan · Darius · CC · Akari · Chloe
PROPOSAL · 1 SEP 2026
3
days to prepare
5
people · maximum team
One team. One loop. One story.

## Slide 2
THE REALITY
This is a 50-hour decision race.
02
FRI 4 SEP
5–8pm
Brief, rules, research, and concept lock. Leave with one direction.
SAT 5 SEP
8am–8pm
Prove the core loop, build it, test it, then freeze scope by 5pm.
SUN 6 SEP
8am–8pm
Make the story undeniable. Submit early. Rehearse until calm.
CONFIRMED
In person · Wilkinson Building G04 · USYD · university students · teams of 3–5
UNKNOWN
2026 brief · rubric weights · pitch length · submission deadline · AI/IP rules · prizes
Rule: prepare the machine now. Do not pre-build the solution.

## Slide 3
WHAT PAST WINNERS REVEAL
The winning shape is narrow, native, and retellable.
03
2025 · 1ST
HOT TOPIC
A redesigned comment experience under videos: one familiar behaviour, three prompts, a clear interaction, and no new destination app.
2025 · 2ND
LLAMALERT
A memorable llama flags misinformation, explains why, then turns learning into a tiny game. Instantly repeatable.
2025 · 3RD
TOUCAN
A lightweight overlay at one moment of need. The team deliberately narrowed to learning, awareness, and convenience.
INFERENCE The judges rewarded a precise intervention in an existing routine — backed by proof and presented as a story.
Not another all-in-one app.

## Slide 4
OUR DOCTRINE
One user. One moment. One hero loop. One story.
04
01
USER
Specific — never ‘everyone’
+
02
MOMENT
A real trigger with pain
+
03
LOOP
Trigger → action → payoff
+
04
PROOF
Observed behaviour, not vibes
+
05
STORY
Repeatable after one sentence
If the idea needs a paragraph before the demo, it is not ready.

## Slide 5
CONCEPT SELECTION
No concept reaches high-fi below 20 / 25.
05
01
Problem
specific + evidenced
1
2
3
4
5
02
Effectiveness
changes behaviour
1
2
3
4
5
03
Innovation
distinct mechanism
1
2
3
4
5
04
Craft
excellent in time
1
2
3
4
5
05
Story
instant recall
1
2
3
4
5
HISTORIC RUBRIC
SUEDE 2024 scored visual communication, problem, solution, innovation, and presentation.

## Slide 6
FIVE OWNERS · ONE TEAM
Clear accountability beats polite overlap.
06
ETHAN
CAPTAIN / PRODUCT
brief · scope · decisions · pitch
DARIUS
RESEARCH / PROOF
interviews · tests · evidence
CC
UX / INTERACTION
flow · states · prototype logic
AKARI
VISUAL / BRAND
system · craft · motion
CHLOE
STORY / SUBMISSION
deck · QA · backups · timing
Swap names after a 20-minute skills audit — keep these five ownership areas.

## Slide 7
1–3 SEPTEMBER
Prepare the operating system — legally.
07
TUE · ALIGN
Register + assign
• confirm 5 registrations • finalise role owners • shared Figma + drive • empty research/deck templates • ask organisers 4 rule questions
WED · REHEARSE
Run the machine
• 90-minute neutral mini-sprint • concept scorecard drill • five-minute interview • lo-fi loop • 60-second pitch • test file permissions
THU · DE-RISK
Lower friction
• pack + charge everything • fonts/tools available offline • travel + 4:15pm arrival • backup file system • stop heavy work by 9pm • sleep

## Slide 8
FRIDAY · UNDERSTAND + CHOOSE
Concept lock within 90 minutes of the brief.
08
5:00
CAPTURE
exact brief · rules · deliverables
5:30
DECODE
user · behaviour · constraint · success
5:45
DIVERGE
six ideas each → cluster to three
6:10
SCORE
kill weakly testable + feature-heavy ideas
6:30
TALK
five rapid user conversations
7:25
LOCK
one line · one loop · one direction
FRIDAY EXIT
everyone says the same one-line product

## Slide 9
SATURDAY · PROVE + BUILD
Test low-fi early. Freeze features at 5pm.
09
08:00
MAP
current journey + 5–7 frame hero loop
09:30
LOW-FI
clickable core
10:30
TEST
3 users · observe, don’t explain
11:15
MENTOR 1
problem / solution logic
12:00
BUILD
mid/high-fi + story in parallel
14:00
TEST 2
comprehension + task success
15:30
POLISH
trust · error · accessibility state
17:00
FREEZE
no new scope
18:15
PITCH 1
timed · brutal critique · backup demo
Saturday exit: a stranger completes the loop, explains the value, and remembers the mechanism.

## Slide 10
SUNDAY · MAKE IT UNDENIABLE
Submission safety first. Polish second.
10
08:00–10:30
STABILISE
Fresh-eyes QA. Finish the deck and submission copy from the same story.
10:30–12:30
ATTACK
Ask a mentor: ‘Why would this not advance?’ Fix only decisive objections.
12:30 ONWARD
REHEARSE
Create a submittable checkpoint, then rehearse both 3- and 5-minute versions.
-90 MIN
A complete, tested submission exists before the official deadline.
Links work in incognito · assets disclosed · backup video on two devices · confirmation captured
After submission: freeze → hydrate → reset → present.

## Slide 11
THE THREE-MINUTE PITCH
Demo the changed behaviour — not a feature tour.
11
0:00
HUMAN MOMENT
put the judge inside the pain
→
0:20
EVIDENCE
what people actually do
→
0:45
ONE LINE
product + memorable mechanism
→
1:00
HERO DEMO
trigger → action → payoff
→
1:50
LEARNING
what testing changed + trust
→
2:15
CREDIBILITY
impact · feasibility · access
→
2:40
CALLBACK
return to the human; land one line
SPEAKER RULE
One lead voice. Others own demo control and Q&A. Record a backup.

## Slide 12
THE KILL LIST
Most teams lose through scope, not talent.
12
no ‘app for everyone’
no more than 3 concepts after hour one
no high-fi before low-fi testing
no feature after Saturday 5pm
no fake evidence or technical claims
no vague ‘AI-powered’ magic
no live demo without backup
no five-person pixel committee
no all-nighter as a strategy
no process-heavy pitch
Before adding anything: which score does this improve?

## Slide 13
THE NEXT 24 HOURS
Win preparation starts with five boring certainties.
13
01
REGISTRATION
All five confirmation emails visible
02
ROLE LOCK
20-minute strengths audit tonight
03
ORGANISER CHECK
brief · deadline · AI/IP · rubric/pitch
04
90-MIN DRILL
run the neutral sprint tomorrow
05
ARRIVAL
Wilkinson G04 by 4:15pm Friday
Target: the clearest tested idea in the room — delivered by the calmest team.

## Slide 14
EVIDENCE + CAVEATS
Current organiser announcements override this deck.
14
2026 OFFICIAL
events.humanitix.com/suede-designaton-2026
SUEDE LIVE LINKS
linktr.ee/suedesociety
2025 OVERVIEW
suede-designathon-2025.devpost.com
2025 RULES
suede-designathon-2025.devpost.com/rules
2025 GALLERY
suede-designathon-2025.devpost.com/project-gallery
2024 RUBRIC
suede-designathon-2024.devpost.com
Research cut-off: 1 Sep 2026 · 2026 brief, rubric, deadline, judges, prizes, and AI/IP rules were not public.